## Executive Dashboard
JasonAI Executive Strategy Tracker
24-MONTH OPERATING SYSTEM ¦ SMB GENERAL CONTRACTORS ¦ WHATSAPP AI ASSISTANT
Overall execution |  |  | Completed tasks |  | KPI gates met |  | Overdue tasks
0% |  |  | 0 |  | 0 |  | 0
Current operating position |  | Pre-start |  |  |  | Update task status, quantity, outcomes, and evidence in Task Tracker. Update gate and goal status in KPI Tracker. All dashboard results roll up automatically.
Phase | Execution | Gates Met | Goals Met | Position
Foundation | 0% | 0 | 0 | Upcoming
Validation | 0% | 0 | 0 | Upcoming
Inflection | 0% | 0 | 0 | Upcoming
Scale | 0% | 0 | 0 | Upcoming
Platform | 0% | 0 | 0 | Upcoming
KPI Type | Execution | Gates Met | Goals Met
PRICING | 0% | 0 | 0
PRODUCT | 0% | 0 | 0
SUCCESS | 0% | 0 | 0
Decision rule: a phase is ready to advance only when its minimum KPI gates are met. Task completion indicates execution effort; gate and goal status indicate business evidence.

## Roadmap
Five-Phase Roadmap
J-CURVE ¦ AUGUST 2026 - JULY 2028 ¦ PHASE PROGRESS ROLLS UP FROM KPI EXECUTION
Phase # | Phase | Start | End | Curve Position | Objective | KPI Gates Met | Execution | Date Position | Advance Readiness
01 | Foundation | 2026-08-01 | 2026-10-31 | INVEST | Deliver useful output fast enough to earn payment. | 0 | 0% | Upcoming | Not Ready
02 | Validation | 2026-11-01 | 2027-01-31 | VALIDATE | Retain teams and prove measurable value. | 0 | 0% | Upcoming | Not Ready
03 | Inflection | 2027-02-01 | 2027-07-31 | PROVE | Use proven ROI to support pricing and retention. | 0 | 0% | Upcoming | Not Ready
04 | Scale | 2027-08-01 | 2028-01-31 | SCALE | Repeat acquisition, onboarding, and retention efficiently. | 0 | 0% | Upcoming | Not Ready
05 | Platform | 2028-02-01 | 2028-07-31 | EXPAND | Expand customer usage and spend over time. | 0 | 0% | Upcoming | Not Ready
Formulas:
Date Position = IF(TODAY()<[Start],"Upcoming",IF(TODAY()>[End],"Complete","Current"))

## KPI Tracker
KPI Tracker
EDIT CURRENT RESULT, GATE STATUS, GOAL STATUS, AND REVIEW DATE ¦ EXECUTION ROLLS UP FROM TASKS
Phase | Period | KPI Type | KPI | Owner | Minimum Gate | Goal | Current Result | Gate Status | Goal Status | Tasks Complete | Total Tasks | Task Summary | Execution % | Next Review
Foundation | AUG-OCT 2026 | PRICING | Customers willing to pay | CEO | 3 pilot customers agree to pay after seeing JasonAI work. | 5 customers willing to pay $10-$25 per month. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Foundation | AUG-OCT 2026 | PRODUCT | Useful-output rate | CTO | 80% of reviewed outputs are useful. | 90% require little or no correction. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Foundation | AUG-OCT 2026 | SUCCESS | Time to first value | COO | Useful output within 15 minutes of onboarding. | Useful output within 5 minutes. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Validation | NOV 2026-JAN 2027 | PRICING | Pilot-to-paid conversion | CEO | 30% pilot-to-paid conversion. | 50% pilot-to-paid conversion. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Validation | NOV 2026-JAN 2027 | PRODUCT | Four-week team retention | CTO | 50% of pilot teams remain active at week four. | 65% of pilot teams remain active at week four. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Validation | NOV 2026-JAN 2027 | SUCCESS | Verified hours saved | COO | 1 verified hour saved per team each week. | 2 verified hours saved per team each week. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Inflection | FEB-JUL 2027 | PRICING | Average revenue per team | CEO | $40 average monthly revenue per team. | $75 average monthly revenue per team. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Inflection | FEB-JUL 2027 | PRODUCT | Eight-week retention | CTO | 60% of teams remain active at week eight. | 75% of teams remain active at week eight. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Inflection | FEB-JUL 2027 | SUCCESS | Customer-confirmed ROI | COO | 70% of customers confirm positive ROI. | 85% of customers confirm positive ROI. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Scale | AUG 2027-JAN 2028 | PRICING | LTV:CAC | CEO | 3x lifetime value to acquisition cost. | 4x lifetime value to acquisition cost. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Scale | AUG 2027-JAN 2028 | PRODUCT | Weekly active teams | CTO | 80% of retained teams are active weekly. | 90% of retained teams are active weekly. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Scale | AUG 2027-JAN 2028 | SUCCESS | Monthly logo churn | COO | Less than 4% monthly logo churn. | Less than 3% monthly logo churn. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Platform | FEB-JUL 2028 | PRICING | Net revenue retention | CEO | 110% net revenue retention. | 120% net revenue retention. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Platform | FEB-JUL 2028 | PRODUCT | Multi-workflow adoption | CTO | 50% of teams use at least two workflows. | 70% of teams use at least two workflows. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%
Platform | FEB-JUL 2028 | SUCCESS | Customer ROI score | COO | 85 out of 100 average ROI score. | 90 out of 100 average ROI score. |  | Not Assessed | Not Assessed | 0 | 4 | 0 / 4 | 0%

## Task Tracker
Task Tracker
UPDATE STATUS, DUE DATE, QUANTITY, RESULT, EVIDENCE, AND NOTES ¦ DASHBOARD AND KPI PROGRESS UPDATE AUTOMATICALLY
Task ID | Phase | Period | KPI Type | KPI | Owner | Task | Status | Due Date | Quantity | Unit | Reported Result | Evidence / Link | Tracked Metrics | Priority | Notes | Completion % | Last Updated
P01-PRI-T01 | Foundation | AUG-OCT 2026 | PRICING | Customers willing to pay | CEO | Recruit five qualified pilot teams. | Not Started | [5 empty] | Qualified pilots recruited (#); Payment commitment rate (%); Willingness-to-pay range ($); Committed monthly recurring revenue ($) | Medium |  | 0%
P01-PRI-T02 | Foundation | AUG-OCT 2026 | PRICING | Customers willing to pay | CEO | Run pricing interviews after live demonstrations. | Not Started | [5 empty] | Qualified pilots recruited (#); Payment commitment rate (%); Willingness-to-pay range ($); Committed monthly recurring revenue ($) | Medium |  | 0%
P01-PRI-T03 | Foundation | AUG-OCT 2026 | PRICING | Customers willing to pay | CEO | Document objections and payment commitments. | Not Started | [5 empty] | Qualified pilots recruited (#); Payment commitment rate (%); Willingness-to-pay range ($); Committed monthly recurring revenue ($) | Medium |  | 0%
P01-PRI-T04 | Foundation | AUG-OCT 2026 | PRICING | Customers willing to pay | CEO | Select the initial paid package and contract terms. | Not Started | [5 empty] | Qualified pilots recruited (#); Payment commitment rate (%); Willingness-to-pay range ($); Committed monthly recurring revenue ($) | Medium |  | 0%
P01-PRO-T01 | Foundation | AUG-OCT 2026 | PRODUCT | Useful-output rate | CTO | Define the useful-output review rubric. | Not Started | [5 empty] | Outputs reviewed (#); Useful-output rate (%); Outputs requiring correction (%); Critical failure rate (%) | Medium |  | 0%
P01-PRO-T02 | Foundation | AUG-OCT 2026 | PRODUCT | Useful-output rate | CTO | Instrument quality and correction tracking. | Not Started | [5 empty] | Outputs reviewed (#); Useful-output rate (%); Outputs requiring correction (%); Critical failure rate (%) | Medium |  | 0%
P01-PRO-T03 | Foundation | AUG-OCT 2026 | PRODUCT | Useful-output rate | CTO | Resolve the highest-frequency failure cases. | Not Started | [5 empty] | Outputs reviewed (#); Useful-output rate (%); Outputs requiring correction (%); Critical failure rate (%) | Medium |  | 0%
P01-PRO-T04 | Foundation | AUG-OCT 2026 | PRODUCT | Useful-output rate | CTO | Complete privacy and audit controls for pilot data. | Not Started | [5 empty] | Outputs reviewed (#); Useful-output rate (%); Outputs requiring correction (%); Critical failure rate (%) | Medium |  | 0%
P01-SUC-T01 | Foundation | AUG-OCT 2026 | SUCCESS | Time to first value | COO | Create the owner onboarding checklist. | Not Started | [5 empty] | Median time to first value (minutes); Onboarding completion rate (%); First-session success rate (%); Setups requiring assistance (%) | Medium |  | 0%
P01-SUC-T02 | Foundation | AUG-OCT 2026 | SUCCESS | Time to first value | COO | Measure setup time for every pilot. | Not Started | [5 empty] | Median time to first value (minutes); Onboarding completion rate (%); First-session success rate (%); Setups requiring assistance (%) | Medium |  | 0%
P01-SUC-T03 | Foundation | AUG-OCT 2026 | SUCCESS | Time to first value | COO | Remove unnecessary onboarding steps. | Not Started | [5 empty] | Median time to first value (minutes); Onboarding completion rate (%); First-session success rate (%); Setups requiring assistance (%) | Medium |  | 0%
P01-SUC-T04 | Foundation | AUG-OCT 2026 | SUCCESS | Time to first value | COO | Collect feedback after the first successful session. | Not Started | [5 empty] | Median time to first value (minutes); Onboarding completion rate (%); First-session success rate (%); Setups requiring assistance (%) | Medium |  | 0%
P02-PRI-T01 | Validation | NOV 2026-JAN 2027 | PRICING | Pilot-to-paid conversion | CEO | Run structured pilot exit and conversion calls. | Not Started | [5 empty] | Completed pilots (#); Paid conversions (# and %); Average initial contract value ($); Median conversion cycle (days) | Medium |  | 0%
P02-PRI-T02 | Validation | NOV 2026-JAN 2027 | PRICING | Pilot-to-paid conversion | CEO | Package verified ROI evidence for each account. | Not Started | [5 empty] | Completed pilots (#); Paid conversions (# and %); Average initial contract value ($); Median conversion cycle (days) | Medium |  | 0%
P02-PRI-T03 | Validation | NOV 2026-JAN 2027 | PRICING | Pilot-to-paid conversion | CEO | Test monthly and annual payment options. | Not Started | [5 empty] | Completed pilots (#); Paid conversions (# and %); Average initial contract value ($); Median conversion cycle (days) | Medium |  | 0%
P02-PRI-T04 | Validation | NOV 2026-JAN 2027 | PRICING | Pilot-to-paid conversion | CEO | Review every lost conversion and update the offer. | Not Started | [5 empty] | Completed pilots (#); Paid conversions (# and %); Average initial contract value ($); Median conversion cycle (days) | Medium |  | 0%
P02-PRO-T01 | Validation | NOV 2026-JAN 2027 | PRODUCT | Four-week team retention | CTO | Define meaningful weekly team activity. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P02-PRO-T02 | Validation | NOV 2026-JAN 2027 | PRODUCT | Four-week team retention | CTO | Build cohort retention reporting. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P02-PRO-T03 | Validation | NOV 2026-JAN 2027 | PRODUCT | Four-week team retention | CTO | Improve reminders and follow-up behaviors. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P02-PRO-T04 | Validation | NOV 2026-JAN 2027 | PRODUCT | Four-week team retention | CTO | Prioritize workflows that drive repeated use. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P02-SUC-T01 | Validation | NOV 2026-JAN 2027 | SUCCESS | Verified hours saved | COO | Establish a pre-JasonAI time baseline. | Not Started | [5 empty] | Verified hours saved per team per week; Customers validating time saved (%); Baseline workflow time (minutes); Post-JasonAI workflow time (minutes) | Medium |  | 0%
P02-SUC-T02 | Validation | NOV 2026-JAN 2027 | SUCCESS | Verified hours saved | COO | Run weekly value check-ins with owners. | Not Started | [5 empty] | Verified hours saved per team per week; Customers validating time saved (%); Baseline workflow time (minutes); Post-JasonAI workflow time (minutes) | Medium |  | 0%
P02-SUC-T03 | Validation | NOV 2026-JAN 2027 | SUCCESS | Verified hours saved | COO | Validate time-saved claims with each account. | Not Started | [5 empty] | Verified hours saved per team per week; Customers validating time saved (%); Baseline workflow time (minutes); Post-JasonAI workflow time (minutes) | Medium |  | 0%
P02-SUC-T04 | Validation | NOV 2026-JAN 2027 | SUCCESS | Verified hours saved | COO | Issue a monthly value summary. | Not Started | [5 empty] | Verified hours saved per team per week; Customers validating time saved (%); Baseline workflow time (minutes); Post-JasonAI workflow time (minutes) | Medium |  | 0%
P03-PRI-T01 | Inflection | FEB-JUL 2027 | PRICING | Average revenue per team | CEO | Launch tiered, value-based pricing. | Not Started | [5 empty] | Average monthly revenue per team ($); Expansion revenue per team ($); Discount rate (%); Realized price by package ($) | Medium |  | 0%
P03-PRI-T02 | Inflection | FEB-JUL 2027 | PRICING | Average revenue per team | CEO | Identify and sell usage-expansion triggers. | Not Started | [5 empty] | Average monthly revenue per team ($); Expansion revenue per team ($); Discount rate (%); Realized price by package ($) | Medium |  | 0%
P03-PRI-T03 | Inflection | FEB-JUL 2027 | PRICING | Average revenue per team | CEO | Track discounts and realized revenue. | Not Started | [5 empty] | Average monthly revenue per team ($); Expansion revenue per team ($); Discount rate (%); Realized price by package ($) | Medium |  | 0%
P03-PRI-T04 | Inflection | FEB-JUL 2027 | PRICING | Average revenue per team | CEO | Package ROI evidence for higher-value tiers. | Not Started | [5 empty] | Average monthly revenue per team ($); Expansion revenue per team ($); Discount rate (%); Realized price by package ($) | Medium |  | 0%
P03-PRO-T01 | Inflection | FEB-JUL 2027 | PRODUCT | Eight-week retention | CTO | Instrument eight-week retention cohorts. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P03-PRO-T02 | Inflection | FEB-JUL 2027 | PRODUCT | Eight-week retention | CTO | Ship the owner dashboard and ROI view. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P03-PRO-T03 | Inflection | FEB-JUL 2027 | PRODUCT | Eight-week retention | CTO | Automate high-value follow-up workflows. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P03-PRO-T04 | Inflection | FEB-JUL 2027 | PRODUCT | Eight-week retention | CTO | Improve context reliability across conversations. | Not Started | [5 empty] | Activated teams by cohort (#); Four- or eight-week retention (%); Weekly active team rate (%); Meaningful workflows per team (#) | Medium |  | 0%
P03-SUC-T01 | Inflection | FEB-JUL 2027 | SUCCESS | Customer-confirmed ROI | COO | Run a structured quarterly ROI review. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P03-SUC-T02 | Inflection | FEB-JUL 2027 | SUCCESS | Customer-confirmed ROI | COO | Flag low-value accounts before renewal. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P03-SUC-T03 | Inflection | FEB-JUL 2027 | SUCCESS | Customer-confirmed ROI | COO | Execute intervention plans for at-risk teams. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P03-SUC-T04 | Inflection | FEB-JUL 2027 | SUCCESS | Customer-confirmed ROI | COO | Publish approved customer case studies. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P04-PRI-T01 | Scale | AUG 2027-JAN 2028 | PRICING | LTV:CAC | CEO | Measure CAC by acquisition channel. | Not Started | [5 empty] | Customer acquisition cost by channel ($); Estimated customer lifetime value ($); LTV:CAC ratio; CAC payback period (months) | Medium |  | 0%
P04-PRI-T02 | Scale | AUG 2027-JAN 2028 | PRICING | LTV:CAC | CEO | Maintain a cohort-based LTV model. | Not Started | [5 empty] | Customer acquisition cost by channel ($); Estimated customer lifetime value ($); LTV:CAC ratio; CAC payback period (months) | Medium |  | 0%
P04-PRI-T03 | Scale | AUG 2027-JAN 2028 | PRICING | LTV:CAC | CEO | Scale only channels above the minimum gate. | Not Started | [5 empty] | Customer acquisition cost by channel ($); Estimated customer lifetime value ($); LTV:CAC ratio; CAC payback period (months) | Medium |  | 0%
P04-PRI-T04 | Scale | AUG 2027-JAN 2028 | PRICING | LTV:CAC | CEO | Launch referral and partner acquisition motions. | Not Started | [5 empty] | Customer acquisition cost by channel ($); Estimated customer lifetime value ($); LTV:CAC ratio; CAC payback period (months) | Medium |  | 0%
P04-PRO-T01 | Scale | AUG 2027-JAN 2028 | PRODUCT | Weekly active teams | CTO | Deliver self-service onboarding. | Not Started | [5 empty] | Paying teams (#); Weekly active teams (# and %); Meaningful workflows per team (#); Inactive or at-risk teams (#) | Medium |  | 0%
P04-PRO-T02 | Scale | AUG 2027-JAN 2028 | PRODUCT | Weekly active teams | CTO | Release vertical workflow templates. | Not Started | [5 empty] | Paying teams (#); Weekly active teams (# and %); Meaningful workflows per team (#); Inactive or at-risk teams (#) | Medium |  | 0%
P04-PRO-T03 | Scale | AUG 2027-JAN 2028 | PRODUCT | Weekly active teams | CTO | Track feature and workflow usage. | Not Started | [5 empty] | Paying teams (#); Weekly active teams (# and %); Meaningful workflows per team (#); Inactive or at-risk teams (#) | Medium |  | 0%
P04-PRO-T04 | Scale | AUG 2027-JAN 2028 | PRODUCT | Weekly active teams | CTO | Meet production reliability targets. | Not Started | [5 empty] | Paying teams (#); Weekly active teams (# and %); Meaningful workflows per team (#); Inactive or at-risk teams (#) | Medium |  | 0%
P04-SUC-T01 | Scale | AUG 2027-JAN 2028 | SUCCESS | Monthly logo churn | COO | Deploy customer health monitoring. | Not Started | [5 empty] | Monthly logo churn (%); At-risk accounts identified (#); Retention interventions completed (%); Accounts saved after intervention (%) | Medium |  | 0%
P04-SUC-T02 | Scale | AUG 2027-JAN 2028 | SUCCESS | Monthly logo churn | COO | Run proactive churn-prevention playbooks. | Not Started | [5 empty] | Monthly logo churn (%); At-risk accounts identified (#); Retention interventions completed (%); Accounts saved after intervention (%) | Medium |  | 0%
P04-SUC-T03 | Scale | AUG 2027-JAN 2028 | SUCCESS | Monthly logo churn | COO | Schedule recurring executive value reviews. | Not Started | [5 empty] | Monthly logo churn (%); At-risk accounts identified (#); Retention interventions completed (%); Accounts saved after intervention (%) | Medium |  | 0%
P04-SUC-T04 | Scale | AUG 2027-JAN 2028 | SUCCESS | Monthly logo churn | COO | Classify every cancellation cause. | Not Started | [5 empty] | Monthly logo churn (%); At-risk accounts identified (#); Retention interventions completed (%); Accounts saved after intervention (%) | Medium |  | 0%
P05-PRI-T01 | Platform | FEB-JUL 2028 | PRICING | Net revenue retention | CEO | Launch expansion and usage-based pricing. | Not Started | [5 empty] | Net revenue retention (%); Expansion monthly recurring revenue ($); Contraction revenue ($); Customer revenue churn (%) | Medium |  | 0%
P05-PRI-T02 | Platform | FEB-JUL 2028 | PRICING | Net revenue retention | CEO | Maintain account-level expansion forecasts. | Not Started | [5 empty] | Net revenue retention (%); Expansion monthly recurring revenue ($); Contraction revenue ($); Customer revenue churn (%) | Medium |  | 0%
P05-PRI-T03 | Platform | FEB-JUL 2028 | PRICING | Net revenue retention | CEO | Develop enterprise and partner packages. | Not Started | [5 empty] | Net revenue retention (%); Expansion monthly recurring revenue ($); Contraction revenue ($); Customer revenue churn (%) | Medium |  | 0%
P05-PRI-T04 | Platform | FEB-JUL 2028 | PRICING | Net revenue retention | CEO | Review net revenue retention monthly. | Not Started | [5 empty] | Net revenue retention (%); Expansion monthly recurring revenue ($); Contraction revenue ($); Customer revenue churn (%) | Medium |  | 0%
P05-PRO-T01 | Platform | FEB-JUL 2028 | PRODUCT | Multi-workflow adoption | CTO | Ship a modular agent and workflow system. | Not Started | [5 empty] | Teams using two or more workflows (%); Workflow adoption by account (%); Active workflows per team (#); Integration-driven activity (%) | Medium |  | 0%
P05-PRO-T02 | Platform | FEB-JUL 2028 | PRODUCT | Multi-workflow adoption | CTO | Add priority business integrations. | Not Started | [5 empty] | Teams using two or more workflows (%); Workflow adoption by account (%); Active workflows per team (#); Integration-driven activity (%) | Medium |  | 0%
P05-PRO-T03 | Platform | FEB-JUL 2028 | PRODUCT | Multi-workflow adoption | CTO | Harden context, access, and permissions. | Not Started | [5 empty] | Teams using two or more workflows (%); Workflow adoption by account (%); Active workflows per team (#); Integration-driven activity (%) | Medium |  | 0%
P05-PRO-T04 | Platform | FEB-JUL 2028 | PRODUCT | Multi-workflow adoption | CTO | Track adoption by workflow and customer segment. | Not Started | [5 empty] | Teams using two or more workflows (%); Workflow adoption by account (%); Active workflows per team (#); Integration-driven activity (%) | Medium |  | 0%
P05-SUC-T01 | Platform | FEB-JUL 2028 | SUCCESS | Customer ROI score | COO | Standardize the customer ROI scorecard. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P05-SUC-T02 | Platform | FEB-JUL 2028 | SUCCESS | Customer ROI score | COO | Benchmark results across account cohorts. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P05-SUC-T03 | Platform | FEB-JUL 2028 | SUCCESS | Customer ROI score | COO | Create account expansion plans from ROI data. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%
P05-SUC-T04 | Platform | FEB-JUL 2028 | SUCCESS | Customer ROI score | COO | Issue recurring executive value reports. | Not Started | [5 empty] | Customers confirming positive ROI (%); Average customer ROI score; Estimated monthly value delivered ($); ROI reviews completed on time (%) | Medium |  | 0%

## Metric Log
Tracked Metrics
ONE DEFINED PERFORMANCE MEASURE PER ROW ¦ UPDATE CURRENT VALUE, FREQUENCY, DATE, SOURCE, AND NOTES
Metric ID | Phase | KPI Type | KPI | Owner | Metric | Frequency | Direction | Unit | Baseline | Current Value | Minimum Gate | Goal | Last Updated | Source / Evidence | Notes
P01-PRI-M01 | Foundation | PRICING | Customers willing to pay | CEO | Qualified pilots recruited (#) | Weekly | Higher is better | # |  |  | 3 pilot customers agree to pay after seeing JasonAI work. | 5 customers willing to pay $10-$25 per month.
P01-PRI-M02 | Foundation | PRICING | Customers willing to pay | CEO | Payment commitment rate (%) | Weekly | Higher is better | % |  |  | 3 pilot customers agree to pay after seeing JasonAI work. | 5 customers willing to pay $10-$25 per month.
P01-PRI-M03 | Foundation | PRICING | Customers willing to pay | CEO | Willingness-to-pay range ($) | Weekly | Higher is better | $ |  |  | 3 pilot customers agree to pay after seeing JasonAI work. | 5 customers willing to pay $10-$25 per month.
P01-PRI-M04 | Foundation | PRICING | Customers willing to pay | CEO | Committed monthly recurring revenue ($) | Weekly | Higher is better | $ |  |  | 3 pilot customers agree to pay after seeing JasonAI work. | 5 customers willing to pay $10-$25 per month.
P01-PRO-M01 | Foundation | PRODUCT | Useful-output rate | CTO | Outputs reviewed (#) | Weekly | Higher is better | # |  |  | 80% of reviewed outputs are useful. | 90% require little or no correction.
P01-PRO-M02 | Foundation | PRODUCT | Useful-output rate | CTO | Useful-output rate (%) | Weekly | Higher is better | % |  |  | 80% of reviewed outputs are useful. | 90% require little or no correction.
P01-PRO-M03 | Foundation | PRODUCT | Useful-output rate | CTO | Outputs requiring correction (%) | Weekly | Higher is better | % |  |  | 80% of reviewed outputs are useful. | 90% require little or no correction.
P01-PRO-M04 | Foundation | PRODUCT | Useful-output rate | CTO | Critical failure rate (%) | Weekly | Lower is better | % |  |  | 80% of reviewed outputs are useful. | 90% require little or no correction.
P01-SUC-M01 | Foundation | SUCCESS | Time to first value | COO | Median time to first value (minutes) | Weekly | Lower is better | minutes |  |  | Useful output within 15 minutes of onboarding. | Useful output within 5 minutes.
P01-SUC-M02 | Foundation | SUCCESS | Time to first value | COO | Onboarding completion rate (%) | Weekly | Higher is better | % |  |  | Useful output within 15 minutes of onboarding. | Useful output within 5 minutes.
P01-SUC-M03 | Foundation | SUCCESS | Time to first value | COO | First-session success rate (%) | Weekly | Higher is better | % |  |  | Useful output within 15 minutes of onboarding. | Useful output within 5 minutes.
P01-SUC-M04 | Foundation | SUCCESS | Time to first value | COO | Setups requiring assistance (%) | Weekly | Higher is better | % |  |  | Useful output within 15 minutes of onboarding. | Useful output within 5 minutes.
P02-PRI-M01 | Validation | PRICING | Pilot-to-paid conversion | CEO | Completed pilots (#) | Weekly | Higher is better | # |  |  | 30% pilot-to-paid conversion. | 50% pilot-to-paid conversion.
P02-PRI-M02 | Validation | PRICING | Pilot-to-paid conversion | CEO | Paid conversions (# and %) | Weekly | Higher is better | # and % |  |  | 30% pilot-to-paid conversion. | 50% pilot-to-paid conversion.
P02-PRI-M03 | Validation | PRICING | Pilot-to-paid conversion | CEO | Average initial contract value ($) | Weekly | Higher is better | $ |  |  | 30% pilot-to-paid conversion. | 50% pilot-to-paid conversion.
P02-PRI-M04 | Validation | PRICING | Pilot-to-paid conversion | CEO | Median conversion cycle (days) | Weekly | Higher is better | days |  |  | 30% pilot-to-paid conversion. | 50% pilot-to-paid conversion.
P02-PRO-M01 | Validation | PRODUCT | Four-week team retention | CTO | Activated teams by cohort (#) | Weekly | Higher is better | # |  |  | 50% of pilot teams remain active at week four. | 65% of pilot teams remain active at week four.
P02-PRO-M02 | Validation | PRODUCT | Four-week team retention | CTO | Four- or eight-week retention (%) | Weekly | Higher is better | % |  |  | 50% of pilot teams remain active at week four. | 65% of pilot teams remain active at week four.
P02-PRO-M03 | Validation | PRODUCT | Four-week team retention | CTO | Weekly active team rate (%) | Weekly | Higher is better | % |  |  | 50% of pilot teams remain active at week four. | 65% of pilot teams remain active at week four.
P02-PRO-M04 | Validation | PRODUCT | Four-week team retention | CTO | Meaningful workflows per team (#) | Weekly | Higher is better | # |  |  | 50% of pilot teams remain active at week four. | 65% of pilot teams remain active at week four.
P02-SUC-M01 | Validation | SUCCESS | Verified hours saved | COO | Verified hours saved per team per week | Weekly | Higher is better |  |  |  | 1 verified hour saved per team each week. | 2 verified hours saved per team each week.
P02-SUC-M02 | Validation | SUCCESS | Verified hours saved | COO | Customers validating time saved (%) | Weekly | Lower is better | % |  |  | 1 verified hour saved per team each week. | 2 verified hours saved per team each week.
P02-SUC-M03 | Validation | SUCCESS | Verified hours saved | COO | Baseline workflow time (minutes) | Weekly | Lower is better | minutes |  |  | 1 verified hour saved per team each week. | 2 verified hours saved per team each week.
P02-SUC-M04 | Validation | SUCCESS | Verified hours saved | COO | Post-JasonAI workflow time (minutes) | Weekly | Lower is better | minutes |  |  | 1 verified hour saved per team each week. | 2 verified hours saved per team each week.
P03-PRI-M01 | Inflection | PRICING | Average revenue per team | CEO | Average monthly revenue per team ($) | Weekly | Higher is better | $ |  |  | $40 average monthly revenue per team. | $75 average monthly revenue per team.
P03-PRI-M02 | Inflection | PRICING | Average revenue per team | CEO | Expansion revenue per team ($) | Weekly | Higher is better | $ |  |  | $40 average monthly revenue per team. | $75 average monthly revenue per team.
P03-PRI-M03 | Inflection | PRICING | Average revenue per team | CEO | Discount rate (%) | Weekly | Higher is better | % |  |  | $40 average monthly revenue per team. | $75 average monthly revenue per team.
P03-PRI-M04 | Inflection | PRICING | Average revenue per team | CEO | Realized price by package ($) | Weekly | Higher is better | $ |  |  | $40 average monthly revenue per team. | $75 average monthly revenue per team.
P03-PRO-M01 | Inflection | PRODUCT | Eight-week retention | CTO | Activated teams by cohort (#) | Weekly | Higher is better | # |  |  | 60% of teams remain active at week eight. | 75% of teams remain active at week eight.
P03-PRO-M02 | Inflection | PRODUCT | Eight-week retention | CTO | Four- or eight-week retention (%) | Weekly | Higher is better | % |  |  | 60% of teams remain active at week eight. | 75% of teams remain active at week eight.
P03-PRO-M03 | Inflection | PRODUCT | Eight-week retention | CTO | Weekly active team rate (%) | Weekly | Higher is better | % |  |  | 60% of teams remain active at week eight. | 75% of teams remain active at week eight.
P03-PRO-M04 | Inflection | PRODUCT | Eight-week retention | CTO | Meaningful workflows per team (#) | Weekly | Higher is better | # |  |  | 60% of teams remain active at week eight. | 75% of teams remain active at week eight.
P03-SUC-M01 | Inflection | SUCCESS | Customer-confirmed ROI | COO | Customers confirming positive ROI (%) | Weekly | Higher is better | % |  |  | 70% of customers confirm positive ROI. | 85% of customers confirm positive ROI.
P03-SUC-M02 | Inflection | SUCCESS | Customer-confirmed ROI | COO | Average customer ROI score | Weekly | Higher is better |  |  |  | 70% of customers confirm positive ROI. | 85% of customers confirm positive ROI.
P03-SUC-M03 | Inflection | SUCCESS | Customer-confirmed ROI | COO | Estimated monthly value delivered ($) | Weekly | Higher is better | $ |  |  | 70% of customers confirm positive ROI. | 85% of customers confirm positive ROI.
P03-SUC-M04 | Inflection | SUCCESS | Customer-confirmed ROI | COO | ROI reviews completed on time (%) | Weekly | Lower is better | % |  |  | 70% of customers confirm positive ROI. | 85% of customers confirm positive ROI.
P04-PRI-M01 | Scale | PRICING | LTV:CAC | CEO | Customer acquisition cost by channel ($) | Weekly | Higher is better | $ |  |  | 3x lifetime value to acquisition cost. | 4x lifetime value to acquisition cost.
P04-PRI-M02 | Scale | PRICING | LTV:CAC | CEO | Estimated customer lifetime value ($) | Weekly | Lower is better | $ |  |  | 3x lifetime value to acquisition cost. | 4x lifetime value to acquisition cost.
P04-PRI-M03 | Scale | PRICING | LTV:CAC | CEO | LTV:CAC ratio | Weekly | Higher is better |  |  |  | 3x lifetime value to acquisition cost. | 4x lifetime value to acquisition cost.
P04-PRI-M04 | Scale | PRICING | LTV:CAC | CEO | CAC payback period (months) | Weekly | Higher is better | months |  |  | 3x lifetime value to acquisition cost. | 4x lifetime value to acquisition cost.
P04-PRO-M01 | Scale | PRODUCT | Weekly active teams | CTO | Paying teams (#) | Weekly | Higher is better | # |  |  | 80% of retained teams are active weekly. | 90% of retained teams are active weekly.
P04-PRO-M02 | Scale | PRODUCT | Weekly active teams | CTO | Weekly active teams (# and %) | Weekly | Higher is better | # and % |  |  | 80% of retained teams are active weekly. | 90% of retained teams are active weekly.
P04-PRO-M03 | Scale | PRODUCT | Weekly active teams | CTO | Meaningful workflows per team (#) | Weekly | Higher is better | # |  |  | 80% of retained teams are active weekly. | 90% of retained teams are active weekly.
P04-PRO-M04 | Scale | PRODUCT | Weekly active teams | CTO | Inactive or at-risk teams (#) | Weekly | Higher is better | # |  |  | 80% of retained teams are active weekly. | 90% of retained teams are active weekly.
P04-SUC-M01 | Scale | SUCCESS | Monthly logo churn | COO | Monthly logo churn (%) | Weekly | Lower is better | % |  |  | Less than 4% monthly logo churn. | Less than 3% monthly logo churn.
P04-SUC-M02 | Scale | SUCCESS | Monthly logo churn | COO | At-risk accounts identified (#) | Weekly | Higher is better | # |  |  | Less than 4% monthly logo churn. | Less than 3% monthly logo churn.
P04-SUC-M03 | Scale | SUCCESS | Monthly logo churn | COO | Retention interventions completed (%) | Weekly | Higher is better | % |  |  | Less than 4% monthly logo churn. | Less than 3% monthly logo churn.
P04-SUC-M04 | Scale | SUCCESS | Monthly logo churn | COO | Accounts saved after intervention (%) | Weekly | Higher is better | % |  |  | Less than 4% monthly logo churn. | Less than 3% monthly logo churn.
P05-PRI-M01 | Platform | PRICING | Net revenue retention | CEO | Net revenue retention (%) | Weekly | Higher is better | % |  |  | 110% net revenue retention. | 120% net revenue retention.
P05-PRI-M02 | Platform | PRICING | Net revenue retention | CEO | Expansion monthly recurring revenue ($) | Weekly | Higher is better | $ |  |  | 110% net revenue retention. | 120% net revenue retention.
P05-PRI-M03 | Platform | PRICING | Net revenue retention | CEO | Contraction revenue ($) | Weekly | Higher is better | $ |  |  | 110% net revenue retention. | 120% net revenue retention.
P05-PRI-M04 | Platform | PRICING | Net revenue retention | CEO | Customer revenue churn (%) | Weekly | Lower is better | % |  |  | 110% net revenue retention. | 120% net revenue retention.
P05-PRO-M01 | Platform | PRODUCT | Multi-workflow adoption | CTO | Teams using two or more workflows (%) | Weekly | Higher is better | % |  |  | 50% of teams use at least two workflows. | 70% of teams use at least two workflows.
P05-PRO-M02 | Platform | PRODUCT | Multi-workflow adoption | CTO | Workflow adoption by account (%) | Weekly | Higher is better | % |  |  | 50% of teams use at least two workflows. | 70% of teams use at least two workflows.
P05-PRO-M03 | Platform | PRODUCT | Multi-workflow adoption | CTO | Active workflows per team (#) | Weekly | Higher is better | # |  |  | 50% of teams use at least two workflows. | 70% of teams use at least two workflows.
P05-PRO-M04 | Platform | PRODUCT | Multi-workflow adoption | CTO | Integration-driven activity (%) | Weekly | Higher is better | % |  |  | 50% of teams use at least two workflows. | 70% of teams use at least two workflows.
P05-SUC-M01 | Platform | SUCCESS | Customer ROI score | COO | Customers confirming positive ROI (%) | Weekly | Higher is better | % |  |  | 85 out of 100 average ROI score. | 90 out of 100 average ROI score.
P05-SUC-M02 | Platform | SUCCESS | Customer ROI score | COO | Average customer ROI score | Weekly | Higher is better |  |  |  | 85 out of 100 average ROI score. | 90 out of 100 average ROI score.
P05-SUC-M03 | Platform | SUCCESS | Customer ROI score | COO | Estimated monthly value delivered ($) | Weekly | Higher is better | $ |  |  | 85 out of 100 average ROI score. | 90 out of 100 average ROI score.
P05-SUC-M04 | Platform | SUCCESS | Customer ROI score | COO | ROI reviews completed on time (%) | Weekly | Lower is better | % |  |  | 85 out of 100 average ROI score. | 90 out of 100 average ROI score.

## Meeting Actions
Meeting Decisions & Actions
CAPTURE EACH DECISION OR COMMITMENT WITH ONE OWNER, MEASURE, AND DEADLINE
Meeting Date | Meeting | Type | Decision / Action | Owner | Due Date | Status | Phase | KPI Type | Success Measure | Evidence / Link | Escalation | Notes
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No
|  | Action |  |  |  | Not Started |  |  |  |  | No

## Meeting Cadence
Executive Meeting Cadence
THREE FOCUSED MEETINGS ¦ 2 HOURS 30 MINUTES PER WEEK ¦ PREPARE, DECIDE, FOLLOW THROUGH
Day | Meeting | Duration | Lead | Purpose | Timeboxed Flow | Required Outputs | Owner Scope
MONDAY | Executive Operating Review | 60 MINUTES | CEO | Set the company priority, inspect the active phase gate, and resolve cross-functional decisions. | 00-05 Restate the phase objective and weekly outcome. 05-20 Review KPI movement, gate risk, and exceptions. 20-40 Decide the two or three issues blocking progress. 40-55 Assign commitments with owner, metric, and date. 55-60 Read back decisions and deprioritized work. | One weekly priority Decision log Named commitments Recorded escalations | Pricing, market selection, revenue, partnerships, capital, and final phase-priority decisions.
WEDNESDAY | Product + Customer Checkpoint | 45 MINUTES | CTO | Turn live customer evidence into product decisions before quality, privacy, or delivery risks compound. | 00-10 Review incidents, quality, and delivery confidence. 10-20 Review the highest-value customer signal. 20-35 Decide fixes, experiments, and scope changes. 35-45 Confirm owners, measures, and communication. | Ranked interventions Acceptance criteria Customer communication Escalation list | Product quality, architecture, delivery, reliability, and safety and privacy risk.
FRIDAY | KPI + Commitments Review | 45 MINUTES | COO | Close the week with verified results, completed task reports, captured learning, and a clean Monday agenda. | 00-15 Score commitments complete, incomplete, or invalid. 15-25 Compare active KPIs with gate and goal. 25-35 Capture evidence and changed assumptions. 35-45 Accept carryovers and draft Monday decisions. | Current dashboard Evidenced work Accepted carryovers Monday decision agenda | Scorecard, customer success, onboarding, action tracking, and meeting follow-through.
Stage | Timing | Coordinator / Lead | Required Practice
BEFORE | 24 HOURS BEFORE | COO coordinates; every KPI owner contributes. | Update KPI results, task reports, quantities, evidence, and tracked metrics. Submit only topics requiring a decision, tradeoff, or escalation. State the desired decision for every agenda item.
DURING | TIMEBOXED | Meeting lead facilitates; CEO resolves company tradeoffs. | Start with the scorecard and exceptions; do not read status updates aloud. Separate facts, assumptions, options, and the requested decision. End every topic with one owner, success measure, and due date.
AFTER | WITHIN 2 HOURS | COO maintains the operating record. | Publish decisions and actions with owners, dates, and measures. Update any changed result, task, phase gate, or priority. Escalate any unresolved blocker older than 48 hours to the CEO.
Operating Rule # | Rule
01 | One directly responsible individual for every action.
02 | No commitment without an owner, metric, and deadline.
03 | Record every decision, rationale, and revisit condition.
04 | Below-minimum metrics take priority over new scope.
05 | Keep routine updates asynchronous.

## Lists & Guide
Workbook Guide & Controlled Lists
EDIT THE TRACKER SHEETS; DO NOT OVERWRITE FORMULA COLUMNS ¦ SOURCE: JASONAI EXECUTIVE STRATEGY
Workflow | How to use it | Status | Priority | Owners | KPI Types | Gate / Goal
Weekly execution | Update task Status, Due Date, Quantity, Reported Result, Evidence, Priority, Notes, and Last Updated. | Not Started | Low | CEO | PRICING | Not Assessed
KPI review | Update Current Result, Gate Status, Goal Status, and Next Review. Task counts and execution are formula-driven. | In Progress | Medium | COO | PRODUCT | Below Gate / Goal
Metric review | Update Current Value, Frequency, Last Updated, Source / Evidence, and Notes for each tracked metric. | Blocked | High | CTO | SUCCESS | Gate Met / Goal Met
Phase advancement | Advance only when all three KPI minimum gates for the phase are marked Gate Met. | Completed | Critical
Meetings | Record every decision, action, risk, or learning in Meeting Actions with one owner, measure, and deadline.
Dashboard | Use the Executive Dashboard for progress, exceptions, and phase readiness. Do not type over dashboard formulas.
Sources and audit trail
Interactive portal | http://localhost:3001/internal/jason-ai
Executive strategy report | http://localhost:3001/internal/jason-ai/executive-strategy
Strategy source | scripts/generate_jasonai_strategy_pdf.py
Tracking source | src/pages/internal/jason-ai/JasonAIInternalPortal.tsx